## User Stories
Story ID | Story Name | As a... (Actor) | I can... (Goal) | Dev Iteration |  | Working? | Notes | Current Developers:
General User
S101 | Job Postings | General User | view Job postings | 2
S102 | Home Page | General User | view the Homepage / Contact Information | 1 |  | Yes | Works/ contact info still needs to be added
S103 | Calendar | General User | View Event Calendar | 2 | Google Cal | No | Nothing | Chris
S104 | Structure | General User | Have every screen in the system implement a common master page | 1 |  | Yes | Works / Picture displays needs to be edited for internal logins (Admins/ Teachers) | Waleed
S105 | Navigation | General User | Use a custom navigation menu that is appropriate for each role | 1 |  | Yes
S106 | User Friendly Error Page/Message | General User | Receive a user friendly error message when a system error occurs. | 3 |  | No | Error exception handling not implemented yet | Iteration 3
S107 | Log In | General User | Log in to the system | 1 |  | Yes | Works / More users for tests still need to be added here!
Logged In User
S201 | Log Out | Logged In User | Log out from the system | 2 |  | Yes | Works? Logout not tested yet! | Iteration 2
Parents/ Kid
S301 | Login | Parent | Login / Logout | 1 |  | Yes | Works / More users for tests still need to be added here!
S302 | Event View | Parent | View upcoming events | 2 | Google Cal | No | Ggl Cal not implemented yet | Chris
S303 | Contact View | Parent | View Contact / Emergency Information | 2
S304 | Details View | Parent | View Accident / Meal report | 2
S305 | Update Form | Parent | Link to document to submit request to update information | 2
Teacher
S401 | Login | Teacher | Login / Logout | 1 |  | Yes | Works / More users for tests still need to be added here!
S402 | Check In Customers | Teacher | Check In / Check Out Kids | 1 |  | Yes | Not completed --> No DB connection , no tests | Wyatt
S403 | View Events | Teacher | View upcoming events | 2 | Google Cal | No | Ggl Cal not implemented yet | Chris
S404 | Update Contacts | Teacher | Maintain Contact Information/ Emergency | 2
S405 | Update Accident/Meals | Teacher | Maintain Accident / Meal reports | 2
S406 | Event Calendar Update | Teacher | Maintain Event Calendar | 2 | Google Cal |  |  | Chris
S407 | Accident Types | Teacher | Maintain Accident Types | 2
S408
System Administrator
| Login | Admin | Login / Logout | 1 |  | Yes | Works / More users for tests still need to be added here!
S501 | Job Postings | Admin | Maintain job postings | 2
S502 | Teacher Functionality | Admin | Inherit all functionality of teacher | 3
S503 | Info Upload | Admin | Upload for parent/kid information | 2 |  |  |  | Waleed
S504 | Accounts Maintenance | Admin | Maintain user accounts | 1 |  | Yes | Works
S505 | Roles | Admin | Create and edit ASP.Net Roles | 1 |  | Yes | Works
S506 | Accounts Maintenance | Admin | Create and edit ASP.Net User accounts | 1 |  | Yes | Works
S507 | Role Functionality | Admin | Assign/change each role's functionality access | 1 |  | Yes | Works
S508
| Test Cases Iteration 1 | [5 empty] | IN PROGRESS! | David
Note on C1: Author: The primary user or stakeholder for the story
Note on D1: Author: The goal that the actor is trying to achieve in the story

## StoriesDetailsIteration1
Story ID | Story Name | As a... (Actor) | I can... (Goal) | Flow | Step | When I... (Action) | Then... (Acceptance Criterion) | Prototyped | Created by Dev | Notes
Gen User
S103 | Calendar | General User | View Event Calendar | Main |  | Request to view the event cal | I see a detailed and updated Google Calenadar | Y | Belzer | See S103.doc
S104 | Structure | General User | Have every screen in the system implement a common master page |  |  | Look at each page individually | common themes and strucutre stay the same for easy orientation | Y | Belzer | See S104.vis
S105 | Navigation | General User | Use a custom navigation menu that is appropriate for each role |  |  | Look at the pages assigned to each role | I see only things accessible and customized to each role | Y | Belzer | See S104.vis
S106 | User Friendly Error Page/Message | General User | Receive a user friendly error message when a system error occurs.
S107 | Log In | General User | Log in to the system |  |  | Log In | the system guides me back to the page initially requested and shows my login status in the top right corner | N | Belzer | See S107.doc
S102 | Home Page | General User | view the Homepage / Contact Information |  |  | View the home page (not logged in) |  | Y | Belzer | S104.vis
Parent
S301 | Login | Parent | Login / Logout | Main |  | Log In | the system guides me back to the page initially requested and shows my login status in the top right corner
S302 | Event View | Parent | View upcoming events |  |  | Request to view the event cal | I see a detailed and updated Google Calenadar
Teacher
S401 | Login | Teacher | Login / Logout | Main |  | Log In | the system guides me back to the page initially requested and shows my login status in the top right corner
S402 | Check In Kids | Teacher | Check In / Check Out Kids |  |  | want to check in newly arrived kids | I want to record the time/date of the log in and see who's all logged in and have the option to check them out any time again
S403 | View Events | Teacher | View upcoming events |  |  | Request to view the event cal | I see a detailed and updated Google Calenadar |  |  | Use Google Calendar Function
Admin
S501 | Login | Admin | Login / Logout | Main
S504 | Info Upload | Admin | Upload for parent/kid information
S505 | Accounts Maintenance | Admin | Maintain user accounts
S506 | Roles | Admin | Create and edit ASP.Net Roles
S507 | Accounts Maintenance | Admin | Create and edit ASP.Net User accounts
S508 | Role Functionality | Admin | Assign/change each role's functionality access
Note on C1: Author: The primary user or stakeholder for the story
Note on D1: Author: The goal that the actor is trying to achieve in the story
Note on E1: Author: Each story consists of a "Main" flow (the happy-day or most commen scenario), plus zero or more "alternative" flows which branch off the Main flow. For example, flow 3a branches off the Main flow at step 3 and flow 3a.5a branches off flow 3a at step 5.
Note on F1: Author: The step number within each flow. Each step is either an Action or an Acceptance Criterion.
Note on G1: Author: The actions performed by the actor.
Note on H1: Author: The expected responses from the system. Each expected response is also an acceptance criterion, and is also the unit of sign-off.
Note on I1: Author: Indicates whether the acceptance criterion has been included in the prototype.
Note on J1: Author: Date the acceptance criterion was agreed by the development team (Chris Clark)

## Cover Sheet
Marina App Functional Specification
Version: | This is a living document and is not formally version controlled.
Accordingly, there is no formal sign-off of the document as a whole. Rather, each "acceptance criterion" is signed off individually (see the "Agreed" columns on the "Details" worksheet).
Overview: | This document (together with a number of supplementary documents) is the functional specification for the project.
This document specifies what the system will do as opposed to how it will do it (i.e. It is not a technical specification).
This document specifies only the changes to the system; it does not specify existing functionality.
Structure: | The functional specification consists of a set of "stories".
Each story describes some aspect of the system's behavior, either functional or non-functional.
A story is the smallest unit of system delivery - a story is either delivered or it is not.
In practice, stories are grouped together and delivered as (time-boxed) "iterations" every 3-4 weeks.
The "Summary" worksheet is an inventory of all the stories, along with various information for each one.
In particular, the "Status" column in the "Summary" worksheet indicates the status of each story, from "being elaborated" right through to "gone live".
The "Details" worksheet contains the detailed specification for each story.
Each story is specified in "use case" format.
See the column heading comments on the "Summary" and "Details" worksheets for further details on the format of the specification.
The "Actors" workheet specifies all actors (users and external systems)

## Actors
Actor Name | Description
General User | Any user, whether logged in or not
Logged In User | Any user who is logged in
Parent/Kid | Logged in user who has a kid in the daycare system, limited to certain rights
Teacher | Logged in user who maintains most activity in system other than job postings and system roles
Sys Admin | Administrator responsible for maintaing all roles and security data and rules within the system